## Sheet1
commonly used card in this screen	Core widgets	usage	Is Completed?	Completed by	extracted as a widget?
welcome	language button	only in this screen 3 times	yes	Shihara	yes
	get started button	commonly used button in the app	yes	Shihara	yes
	skip button	only in this screen 1 time	yes	Shihara	no
	image(svg)	only in this screen 1 time	no	In progress – shihara

login	number input with 075 prefix	used in few different screens	yes	Shihara	yes
	promo code input field	used in few different screens	yes	shihara	in progress
	next button	commonly used button in the app	yes	shihara	no

OTP confirm	OTP code input field	used in few different screens	yes	shihara	in progress

manage connection	connection card	use as a common list widget inside this screen	yes	shihara	yes

add/edit connection	number input with 075 prefix	used in few different screens	yes	shihara	yes
	name input field	used in few different screens	yes	shihara	in progress
	proceed button	commonly used button in the app	yes	shihara	yes

add/edit connection verify	verification code input field	used in few different screens	yes	shihara	yes
	complete button	commonly used button in the app	yes	shihara	yes

notification screen	notification card	use as a common list widget inside this screen	yes	shihara	yes
	delete button	commonly used button in the app	yes	shihara	yes

notification view(notification 3)	image banner	only in this screen 1 time	N/A	N/A	N/A
	action button	commonly used button in the app	yes	shihara	no

side menu	header	only in this screen 1 time	yes	shihara	yes
	menu item – prepaid	use as a common list widget inside this screen	yes	shihara	yes
	menu item – postpaid	use as a common list widget inside this screen	no	In progress - shihara	no

dashboard footer	footer menu - prepaid	only used in footer	N/A	N/A	N/A
	footer menu – postpaid	only used in footer	N/A	N/A	N/A

dashboard contacts	contacts card	use as a common list widget inside this widget
	manage connection button	commonly used button in the app	yes	shihara	yes

Packs & Reload	flash deals carousel	use in home screen also	yes	shihara	yes
	packages card	used in few different screens	in progress	shihara	no
	image banner	use in home screen also	yes	shihara	yes

Entertainment – Movie box	movie poster top carousel	only in this screen 1 time	N/A	N/A	N/A
	single movie card	commonly used list card in the app	N/A	N/A	N/A

Entertainment – See All T1	tab navigator	only in this screen 1 time	yes	shihara	yes
	single movie card	commonly used list card in the app	N/A	N/A	N/A

Entertainment – Services type 2	services card	commonly used list item in the tab	N/A	N/A	N/A
	service card items	commonly used list item in the tab	N/A	N/A	N/A

Entertainment – My Services	my services card	can used the same one on Entertainment – Services type 2	N/A	N/A	N/A
	my service card items	commonly used list item in the tab	N/A	N/A	N/A

Error handling one	pop up model	looks like common message pop up	N/A	N/A	N/A

Error handling two	no internet banner	N/A	N/A	N/A	N/A

Dashboard language selection	language card	commonly used list card in the model	yes	shihara	yes

My profile	background stack widget	only in this screen 1 time	N/A	N/A	N/A
	avatar	used in few different screens	N/A	N/A	N/A
	Facebook connect banner	only in this screen 1 time	N/A	N/A	N/A
	input field	commonly used button in the screen	N/A	N/A	N/A
	Rounded button with icon	commonly used button in the app	N/A	N/A	N/A

My profile edit name	input field	commonly used input field in the app	yes	shihara	yes
	save button	commonly used button in the app	yes	shihara	yes

My interested	Rounded button with icon	commonly used button in the app	N/A	N/A	N/A
	save button	commonly used button in the app	yes	shihara	yes

Airtel Thanks	banner	only in this screen in two tabs	N/A	N/A	N/A
	Benefit card	commonly used card in this screen	N/A	N/A	N/A
	earn more card	commonly used card in this screen	N/A	N/A	N/A

Payment method pop up	payment method card	use few time in this pop up	N/A	N/A	N/A
	proceed button	commonly used button in the app	yes	shihara	yes

package detail pop up – regular	active button	commonly used button in the app	yes	shihara	yes
	detail card	commonly used row in this model	N/A	N/A	N/A

package detail pop up – combopack	active button	commonly used button in the app	yes	shihara	yes
	detail card	can use the package detail pop up – regular detail card	N/A	N/A	N/A

Reload prepaid	number input with 075 prefix	commonly used in the app	yes	shihara	yes
	tab navigator with button	used in few different screens	yes	shihara	yes
	quick reload picker (scroll)	used in few different screens	yes	shihara	yes
	number input with Rs. prefix	only in this screen 1 time	N/A	N/A	N/A
	disabled grey button	commonly used button in the screen	N/A	N/A	N/A
	reload history card	can use the same one in service tab card	N/A	N/A	N/A

Invite friends	promo code display card	only in this screen 1 time	N/A	N/A	N/A
	invite friends button	commonly used button in the app	yes	shihara	yes

IDD – Prepaid	roaming information top banner	only in this screen 1 time	N/A	N/A	N/A
	package card	commonly used card in this app	yes	shihara	yes
	roaming cards	can use the same one in service tab card	N/A	N/A	N/A

Get help	help card	can use the same one in service tab card	N/A	N/A	N/A

E-Services	E-services card	commonly used card in this screen	N/A	N/A	N/A

Locate us	search bar	only in this screen 1 time	N/A	N/A	N/A
	service type button	Used 2 times in this screen	N/A	N/A	N/A
	map view	only in this screen 1 time	N/A	N/A	N/A
	pop up module to navigate	only in this screen 1 time	N/A	N/A	N/A

Error handling three	payment reject pop up	only in this screen 1 time	N/A	N/A	N/A

reload prepaid	number input with 075 prefix	used in few different screens	yes	shihara	yes
	disabled grey button	used in few different screens	N/A	N/A	N/A
	payment history card	used in few different screens	N/A	N/A	N/A
	tab navigator	used in few different screens	yes	shihara	yes
	amount input with Rs. prefix	used in few different screens	N/A	N/A	N/A

Dashboard – prepaid/pospaid	main carousel	used in this screen	in progress	shihara	yes
	connection status button	used in this screen	yes	shihara	yes
	airtel thanks button	used in this screen	yes	shihara	yes
	rounded data details	used in this screen	in progress	shihara	in progress
	horizontal data details	used in this screen	in progress	shihara	in progress
	package cards	common widget	in progress	shihara	in progress
	flash deals carousel	used in some other screens	yes	shihara	yes
	special offer bar	only in this screen 1 time	yes	shihara	yes
	recommended data add ons card	commonly used list card in the screen	yes	shihara	yes
	bottom banner	used in some other screens	yes	shihara	yes
	no packs available	only in this screen 1 time	in progress	shihara	in progress
	paybill	only in this screen 1 time	in progress	shihara	in progress

Dashboard – FAB	FAB widget	available though the app	N/A	N/A	N/A

My balance	money/data card	commonly used card in this screen	N/A	N/A	N/A

FAQ	rounded red button	Used 3 times in this screen	N/A	N/A	N/A
	red button with social media icon	Used 2 times in this screen	N/A	N/A	N/A
	question card	commonly used card in this screen	N/A	N/A	N/A

My account – my bill	bill card	commonly used card in this screen	N/A	N/A	N/A
	bill plan card	commonly used card in this screen	N/A	N/A	N/A

Manage services	service card	can use the package detail pop up – regular detail card	N/A	N/A	N/A

manage services – register email	input field	commonly used input field in the app	yes	shihara	yes
	proceed button	commonly used button in the app	yes	shihara	yes

Error handling five	email update banner	only in this screen 1 time	N/A	N/A	N/A

Give feedback	emoji row – colored	only in this screen 1 time	N/A	N/A	N/A
	text area	common widget	N/A	N/A	N/A
	submit button	commonly used button in the app	yes	shihara	yes
	emoji row – Black and White	only in this screen 1 time	N/A	N/A	N/A

Service request	image picker	only in this screen 1 time	N/A	N/A	N/A
	text area	common widget	N/A	N/A	N/A
	send button	commonly used button in the app	yes	shihara	yes

My account – summary 2	button	commonly used button in the app	yes	shihara	yes

force update flutter	update bottom notification card	common widget	N/A	N/A	N/A

IDD – Postpaid	active button	commonly used button in the app	yes	shihara	yes
	IDD rates card	can used the same one in prepaid	N/A	N/A	N/A

Active roaming	date picker	Used 2 times in this screen	N/A	N/A	N/A
	input field	common widget	yes	shihara	yes
	request button	commonly used button in the app	yes	shihara	yes

My usage – data	usage card	commonly used card in this screen	N/A	N/A	N/A
	voice card	can used usage card	N/A	N/A	N/A
	sms card	commonly used card in this screen	N/A	N/A	N/A